## Scenario Brief
CAREBOT HEALTH - SCENARIO BRIEF
Company: | CareBot Health — hospital network (1,500 employees)
System Name: | DiagnosAI
System Purpose: | GenAI clinical decision support system that analyzes patient symptoms, lab results, and medical history to suggest diagnoses and treatment options for emergency department physicians.
Deployment Status: | Deployed 6 months ago; no formal risk assessment conducted
Recent Incident: | Near-miss incident where the system suggested an incorrect drug interaction for a patient with a rare allergy
Regulatory Context: | FDA clinical decision support guidance, HIPAA, EU AI Act (High-Risk under Annex III — AI in healthcare), NIST AI RMF applicable
COLOR LEGEND
Blue | Header information
Green | Pre-filled scenario context
Light Blue | Pre-filled reference data
Light Pink | Fill live during session (with hints)
Yellow | Reference material

## Risk Register
Risk ID | NIST AI RMF Function | Risk Category | Risk Description | Risk Owner | Impact (1-5) | Likelihood (1-5) | Risk Score | Risk Level | Mitigation Strategy | Priority | Status | Target Date
R001 | Measure | Technical | Diagnostic accuracy degradation: DiagnosAI performance drops as new disease variants emerge that weren't in training data | Chief Medical Informatics Officer | 5 | 3 |  |  | Implement quarterly model revalidation against updated clinical databases, incorporate new disease variant data, establish model performance monitoring KPIs | Critical | Open | TBD
R002 | Govern | Ethical | Diagnostic bias: System shows lower accuracy for underrepresented patient demographics (elderly, rare conditions) | Ethics Officer | 4 | 4 |  |  | Conduct demographic-stratified accuracy audits quarterly, engage with underrepresented community stakeholders, retrain model on balanced datasets | Critical | Open | TBD
R003 | Map | Legal | Hint: HIPAA violation, patient data exposure, unauthorized PHI access | Privacy Officer | [Your response here] | [Your response here] |  |  | [Your response here] | [Your response here] | [Your response here] | [Your response here]
R004 | Manage | Operational | Hint: System downtime during critical care, ER unavailability, clinician fallback | IT Infrastructure Manager | [Your response here] | [Your response here] |  |  | [Your response here] | [Your response here] | [Your response here] | [Your response here]
R005 | Measure | Technical | Hint: Drug interaction false negatives, rare allergy detection (near-miss incident) | Pharmacology Lead | [Your response here] | [Your response here] |  |  | [Your response here] | [Your response here] | [Your response here] | [Your response here]
R006 | Govern | Ethical | Hint: Explainability issues, physician understanding of AI suggestions, informed consent | Chief Medical Officer | [Your response here] | [Your response here] |  |  | [Your response here] | [Your response here] | [Your response here] | [Your response here]
R007 | Hint: GenAI-specific risk | Technical | Hint: Hallucinated clinical recommendations, factually incorrect diagnoses, misleading treatment suggestions | Medical Education Director | [Your response here] | [Your response here] |  |  | [Your response here] | [Your response here] | [Your response here] | [Your response here]

## Scoring Rubric
IMPACT SCALE (1-5)
1 | Low: Minimal direct patient harm; incident contained quickly
2 | Minor: Limited patient harm; short recovery period
3 | Moderate: Significant patient harm; extended recovery; regulatory notice possible
4 | High: Severe patient harm; hospitalization; regulatory investigation
5 | Critical: Patient death; mass harm; permanent system failure; criminal liability
LIKELIHOOD SCALE (1-5)
1 | Remote: Unlikely in the next 12 months; legacy issues only
2 | Low: May occur once in 2-3 years; requires specific condition
3 | Moderate: Likely within 12 months; similar incidents elsewhere
4 | High: Probable within 12 months; emerging pattern detected
5 | Critical: Almost certain within 12 months; immediate threat
RISK LEVEL MATRIX
Critical | Risk Score >= 15 — Executive escalation, immediate action required
High | Risk Score 10-14 — Senior management review, action plan within 30 days
Medium | Risk Score 5-9 — Department review, action plan within 90 days
Low | Risk Score < 5 — Monitor, action only if emerging pattern

## NIST AI RMF Reference
NIST AI RMF: 4 Core Functions
Function | Description | Key Activities | Example for CareBot
Govern | Establish governance structures, policies, and accountability for AI systems | Define roles/responsibilities, establish AI ethics committees, create AI governance policies, ensure board-level AI risk oversight | CareBot: Establish AI governance committee, define roles (Chief Medical Officer, Ethics Officer, CMIO), create policies for AI use in clinical settings
Map | Identify context, application domain, and potential risks for AI systems | Identify stakeholders, define use cases and boundaries, map regulatory landscape, document existing risks and control gaps | CareBot: Identify affected parties (physicians, patients, nurses), map FDA, HIPAA, EU AI Act requirements, identify patient safety risks
Measure | Analyze, monitor, and assess AI system performance, risks, and impact | Collect performance data, evaluate model accuracy across demographics, monitor for bias, conduct ongoing testing | CareBot: Monitor diagnostic accuracy over time, audit for demographic bias, track model drift, test against new disease variants
Manage | Treat identified risks through controls, mitigation, and ongoing monitoring | Implement technical controls, establish incident response, manage change, establish KPIs and monitoring, create remediation plans | CareBot: Deploy explainability module, establish drug interaction database controls, create physician training program, establish downtime protocols