## Scenario Brief
DataVault Analytics — ISO/IEC 42001 Gap Analysis (Solution)
Company Profile:
Organization: DataVault Analytics (350 employees)
Industry: Data Analytics & Business Intelligence
Current Certification: ISO 27001 (Data Security)
Primary AI Systems:
1. InsightEngine — Generative AI for automated report writing from enterprise data
2. AnomalyDetect — Real-time anomaly detection in financial transaction data for banking clients
Certification Goal: ISO/IEC 42001 within 12 months
Critical Incident: InsightEngine hallucinated financial figures in a client report, causing reputational damage and triggering client audit
Current State: ISO 27001 certified for data security, but no formal AI governance framework, no AI-specific policies, and no systematic AI risk management

## Gap Analysis Checklist
Control ID | Clause | Control Area | Control Description | Current State | Evidence Available | Gap Description | Readiness Score | Priority | Remediation Action | Owner | Target Date
C5.1.1 | 5.1 | AI Policy | Leadership commitment to AI governance | Partial | Partial evidence | CEO memo exists but no formal AI policy document | 2 | High | Draft formal AI policy document with board approval | CTO | 2026-04-30
C6.1.1 | 6.1 | Planning | AI risk assessment methodology documented | Not Started | No evidence | No documented AI risk assessment methodology | 1 | Critical | Develop AI risk assessment framework | Risk Officer | 2026-03-31
C8.1.1 | 8.1 | Operations | AI lifecycle management processes | Partial | Partial | Ad-hoc process for InsightEngine but not for AnomalyDetect | 2 | High | Standardize lifecycle management for all AI systems | Ops Manager | 2026-05-15
C5.1.2 | 5.1 | AI Policy | Documented AI policy covering ethical principles and compliance | Not Started | No evidence | No AI ethics or compliance policy document | 1 | Critical | Create comprehensive AI policy aligned with ISO 42001 | CTO | 2026-04-15
C5.2.1 | 5.2 | AI Policy | Roles and responsibilities for AI governance | Initiated | Partial — job descriptions exist | Job descriptions lack AI governance responsibilities | 3 | High | Define AI governance roles and RACI matrix | HR Manager | 2026-04-30
C5.2.2 | 5.2 | AI Policy | Competence assessment for AI team members | Not Started | No evidence | No competence framework for AI professionals | 1 | High | Develop competence matrix and training plan | Chief Data Officer | 2026-05-31
C6.1.2 | 6.1 | Planning | Risk documentation for InsightEngine and AnomalyDetect | Initiated | Partial — post-mortem from hallucination only | Hallucination risk identified post-incident but not systematic | 2 | Critical | Conduct formal risk assessment for both AI systems | Risk Officer | 2026-03-31
C6.2.1 | 6.2 | Planning | AI objectives aligned with business strategy | Partial | Partial — strategy docs exist, no AI targets | AI quality targets not in client SLAs | 2 | High | Align AI objectives with client SLAs | Product Manager | 2026-04-30
C6.3.1 | 6.3 | Planning | Change management for AI model updates | Not Started | No evidence | Model updates deployed without formal controls | 1 | Critical | Implement change management with approval gates and rollback | Ops Manager | 2026-04-15
C7.1.1 | 7.1 | Support | Resources allocated for AI governance | Initiated | Partial — dev budget exists, no governance budget | Governance has zero dedicated resources | 2 | High | Allocate dedicated AI governance resources | CTO | 2026-05-15
C7.2.1 | 7.2 | Support | Training on AI ethics, bias, hallucination mitigation | Not Started | No evidence | No formal AI governance training program | 1 | Critical | Develop mandatory AI ethics and governance training | Chief Data Officer | 2026-05-31
C7.3.1 | 7.3 | Support | AI awareness program for all employees | Not Started | No evidence | AI risk awareness limited to technical team | 2 | High | Launch company-wide AI risk awareness campaign | Communications Manager | 2026-06-30
C7.4.1 | 7.4 | Support | Documentation management for AI artifacts | Initiated | Partial — Git for code, no model cards/dataset docs | Model versions in Git but no centralized AI docs | 2 | High | Implement AI artifact management system | Data Engineer | 2026-05-31
C8.2.1 | 8.2 | Operations | AI impact assessment | Not Started | No evidence | Hallucination impact never formally assessed | 1 | Critical | Develop and conduct impact assessments for all AI systems | Risk Officer | 2026-04-15
C8.3.1 | 8.3 | Operations | Third-party AI component governance | Initiated | Partial — vendor contracts, no AI-specific SLAs | Third-party NLP APIs used without vendor AI assessment | 2 | High | Create vendor assessment criteria and AI-specific SLAs | Procurement Manager | 2026-05-15
C9.1.1 | 9.1 | Performance | Monitoring hallucination, accuracy, bias | Initiated | Partial — basic accuracy dashboards only | No hallucination or bias monitoring | 2 | Critical | Build comprehensive monitoring dashboard | Chief Data Officer | 2026-04-30
C9.2.1 | 9.2 | Performance | Internal audit program for AI systems | Not Started | No evidence | Governance gaps found by client audit, not internally | 1 | High | Develop quarterly internal audit program | Audit Manager | 2026-06-15
C10.1.1 | 10.1 | Improvement | Root cause analysis and corrective action after incidents | Initiated | Partial — informal incident notes only | Incident handled informally, no formal CAPA | 2 | Critical | Implement formal CAPA process and incident tracking | Risk Officer | 2026-04-30
C6.1.3 | 6.1 | Planning | Training Data Provenance and Quality Assessment (GenAI) | Not Started | No data provenance tracking | 1
C8.1.2 | 8.1 | Operations | Prompt and Input Governance (GenAI) | Not Started | No standardized prompts or validation | 1
C8.2.2 | 8.2 | Operations | Output Verification and Validation Gates (GenAI) | Not Started | No output verification process | 1
Note on E2: CEO issued a memo post-audit but there's no board-level commitment or governance charter. Partial because intent exists but formal structures don't.
Note on F2: CEO memo from Jan 2026. No board resolution, governance charter, or committee terms of reference.
Note on G2: ISO 42001 Clause 5.1 requires demonstrable leadership commitment through policy, resources, and accountability — a memo alone is insufficient.
Note on H2: Score 2 (Initiated): Leadership awareness exists but formal commitment mechanisms not in place.
Note on I2: High: Leadership commitment is foundational — without it, other controls lack authority. Not Critical because some intent exists.
Note on J2: Need to escalate from a CEO memo to a board-approved AI governance policy covering scope, principles, and accountability.
Note on K2: CTO owns technology strategy and is best positioned to draft the policy with legal and compliance input.
Note on L2: 2 months for drafting, stakeholder review, and board approval.
Note on E3: No documented risk methodology. The hallucination was handled reactively, not through systematic risk framework.
Note on F3: No risk assessment templates, methodologies, or documented procedures for AI-specific risks.
Note on G3: Clause 6.1 requires a risk-based approach. DataVault has no systematic way to identify or assess AI risks like hallucination, bias, or data poisoning.
Note on H3: Score 1 (Not Started): Complete absence of AI risk assessment capability.
Note on I3: Critical: The hallucination showed real harm from unmanaged risk. Most fundamental gap.
Note on J3: Framework should cover AI-specific risk categories (hallucination, bias, drift, data quality) with scoring tailored to DataVault's systems.
Note on K3: Risk Officer leads methodology; Data Science provides AI-specific risk input.
Note on L3: 1 month — urgent. Basic framework needed before other planning activities.
Note on E4: InsightEngine has informal pipeline but AnomalyDetect has minimal documentation. Neither has formal validation gates.
Note on F4: GitHub repos and deployment scripts exist but no formal lifecycle docs, validation criteria, or monitoring procedures.
Note on G4: Clause 8.1 requires documented lifecycle for ALL AI systems. Having it for one but not the other is a significant gap.
Note on H4: Score 2 (Initiated): Some processes for InsightEngine but informal and don't cover AnomalyDetect.
Note on I4: High: Lifecycle gaps contributed to hallucination — the model update lacked validation gates.
Note on J4: Unified lifecycle framework covering design, development, testing, validation, deployment, monitoring, and retirement for both systems.
Note on K4: ML Ops Manager owns deployment pipeline and is best positioned to formalize the lifecycle.
Note on L4: 3.5 months for documenting current state, designing target lifecycle, implementing for both systems.
Note on E5: No formal AI ethics policy exists. ISO 27001 policies cover data security but not AI-specific ethics, fairness, or transparency.
Note on F5: ISO 27001 policies handle data security but nothing addresses AI ethics, bias prevention, or transparency.
Note on G5: Clause 5.1 requires an AI policy addressing ethical principles. Without it, no formal guidance for developers on AI ethics decisions.
Note on H5: Score 1 (Not Started): No AI-specific policy despite operating two production AI systems.
Note on I5: Critical: Without an AI policy, there's no ethical framework governing how InsightEngine and AnomalyDetect are developed and operated.
Note on J5: Policy should cover: FATE principles, acceptable use, bias prevention, transparency, human oversight, compliance obligations.
Note on K5: CTO with input from Legal (compliance), Data Science (feasibility), Ethics advisors.
Note on L5: Urgent — 1.5 months. Policy must be in place before other governance activities can reference it.
Note on E6: Some job descriptions mention AI but no formal governance roles. During hallucination incident, unclear who had authority to halt the system.
Note on F6: Job descriptions for data scientists exist but no governance committee, RACI matrix, or escalation authority.
Note on G6: Clause 5.2 requires clear roles. Incident exposed that nobody had formal authority for governance decisions about InsightEngine.
Note on H6: Score 3 (Initiated): Some role awareness exists but governance-specific responsibilities aren't formally assigned.
Note on I6: High: Hallucination showed consequences of unclear accountability. Need clear ownership before next incident.
Note on J6: Create RACI matrix for AI governance. Appoint AI Governance Officer. Define escalation paths for incidents.
Note on K6: HR owns role definitions and organizational design with input from CTO.
Note on L6: 2 months for role design, appointment, and communication.
Note on E7: No documented competence requirements. Team hired for technical skills but no assessment of governance, ethics, or risk competence.
Note on F7: No competence framework, skill matrices, or formal assessments for AI-specific competencies.
Note on G7: ISO 42001 requires demonstrated competence. Team may be technically skilled but governance/ethical competence isn't assessed.
Note on H7: Score 1 (Not Started): No competence framework for AI-specific skills beyond general development.
Note on I7: High: AI teams need to understand risks. Hallucination could have been caught with better quality awareness.
Note on J7: Framework covering: AI development, testing/validation, ethics awareness, risk identification, bias detection, incident response.
Note on K7: CDO understands technical competencies needed, can work with HR for assessment framework.
Note on L7: 3 months to design framework, assess current team, develop training for gaps.
Note on E8: Post-mortem done after hallucination but risks aren't systematically identified or documented for either system.
Note on F8: Post-mortem report from hallucination exists but it's a one-off, not systematic documentation.
Note on G8: Reactive risk identification isn't sufficient. ISO 42001 requires proactive, systematic risk documentation covering all systems and categories.
Note on H8: Score 2 (Initiated): Some risk awareness from incident but no systematic approach.
Note on I8: Critical: Risks that aren't documented can't be managed. AnomalyDetect's false positive risk in banking is also unmanaged.
Note on J8: Document risks for both systems: hallucination, bias, data quality, model drift, security, privacy, third-party dependency.
Note on K8: Risk Officer leads methodology; Data Science provides AI-specific risk input per system.
Note on L8: Same urgent timeline as C6.1.1 — risk documentation depends on methodology being in place.
Note on E9: Business objectives exist (grow revenue, expand clients) but aren't formally linked to AI quality targets.
Note on F9: Business strategy documents exist but don't reference AI governance. Client SLAs lack AI-specific quality metrics.
Note on G9: InsightEngine serves client reports directly — AI quality should be in SLAs. Neither system has formal quality commitments.
Note on H9: Score 2 (Initiated): Business strategy exists but connection to AI governance is missing.
Note on I9: High: Misaligned objectives led to prioritizing features over governance — contributing to hallucination.
Note on J9: Define measurable AI objectives (accuracy targets, hallucination limits, bias thresholds) and embed in client contracts.
Note on K9: Product Manager bridges business strategy and AI capabilities, owns client commitments.
Note on L9: 2 months to review strategy, define AI objectives, update client agreements.
Note on E10: No formal change management. InsightEngine model updated without approval, testing, or rollback — leading to hallucination.
Note on F10: No change advisory board, approval workflows, pre-deployment testing, or rollback procedures.
Note on G10: Root cause of hallucination. Model updates went to production without validation gates, approval, or rollback capability.
Note on H10: Score 1 (Not Started): Complete absence of change management for AI systems.
Note on I10: Critical: Uncontrolled model changes directly caused the hallucination. This is a root cause fix.
Note on J10: Change advisory process: impact assessment → testing → approval → staged deployment → monitoring → rollback.
Note on K10: ML Ops Manager owns deployment pipeline, should implement change control gates.
Note on L10: Urgent — 1.5 months. Addresses direct cause of hallucination.
Note on E11: Development well-funded (~40 staff) but governance, compliance, oversight have zero dedicated resources.
Note on F11: Budget for AI development documented but no line item for governance, compliance, or risk management.
Note on G11: 350 employees with ~40 in AI development but 0 dedicated to governance. ISO 42001 requires adequate resources.
Note on H11: Score 2 (Initiated): Resources exist for AI but entirely allocated to development, not governance.
Note on I11: High: Governance activities all need resources. Without budget, other controls can't be implemented.
Note on J11: Need: AI Governance Officer, training budget, monitoring/documentation tools, external audit costs.
Note on K11: CTO can advocate for governance budget with board — business case clear after incident.
Note on L11: 2.5 months to develop business case, get approval, begin allocation.
Note on E12: No formal training on AI risks, ethics, or quality. Team learns on the job without structured guidance.
Note on F12: No training curriculum, completion records, or certification tracking for AI competencies.
Note on G12: After hallucination, no training provided on prevention. Team lacks structured learning on AI governance.
Note on H12: Score 1 (Not Started): Complete absence of AI governance training.
Note on I12: Critical: Competent staff are first line of defense. Hallucination might have been caught with better quality awareness.
Note on J12: Training covering: ethics principles, bias detection, hallucination awareness, quality assurance, incident reporting.
Note on K12: CDO understands technical content, partners with L&D for delivery.
Note on L12: 3 months for curriculum development, pilot, and rollout.
Note on E13: Beyond technical team, employees don't understand AI system limitations. Client-facing staff couldn't explain the hallucination.
Note on F13: No awareness materials, intranet content, or presentations on AI risks.
Note on G13: Client-facing staff deliver InsightEngine reports without understanding hallucination risks — couldn't explain to clients.
Note on H13: Score 2 (Initiated): Technical team aware from incident but no company-wide program exists.
Note on I13: High: Client-facing teams need to understand AI limitations to manage expectations and report concerns.
Note on J13: All-hands presentation, intranet resources, quarterly updates, role-specific guidance for client-facing staff.
Note on K13: Communications drives awareness with content from AI governance team.
Note on L13: 4 months for multi-phase awareness rollout.
Note on E14: Versions tracked in Git but no centralized system for model cards, dataset docs, training provenance, or decision logs.
Note on F14: GitHub repos with code versioning. Model cards, dataset docs, governance decisions scattered or missing.
Note on G14: Git handles code but ISO 42001 needs comprehensive documentation — model cards, dataset provenance, bias assessments, deployment records.
Note on H14: Score 2 (Initiated): Version control exists for code but comprehensive AI documentation management absent.
Note on I14: High: Undocumented artifacts make auditing and troubleshooting (like the hallucination) very difficult.
Note on J14: Central repository for: model cards, dataset docs, training provenance, bias assessments, deployment records, governance decisions.
Note on K14: Data Engineering builds the infrastructure with governance requirements from compliance.
Note on L14: 3 months to evaluate tools, design schema, implement system.
Note on E15: No formal impact assessments despite InsightEngine directly affecting client financial reports.
Note on F15: No impact reports, harm analyses, or risk-benefit evaluations.
Note on G15: Hallucination proved real harm occurs. ISO 42001 requires proactive impact assessment before deployment, not reactive after incidents.
Note on H15: Score 1 (Not Started): No assessments despite systems with clear harm potential.
Note on I15: Critical: Both systems can cause significant harm — InsightEngine to finances, AnomalyDetect to banking accuracy.
Note on J15: Template covering: stakeholder identification, harm categories (financial, reputational, operational), likelihood, severity, mitigation.
Note on K15: Risk Officer leads with input from Product (client impact) and Legal (regulatory exposure).
Note on L15: Urgent — 1.5 months. Impact assessments should have been done pre-deployment.
Note on E16: InsightEngine uses third-party NLP APIs — no formal vendor assessments, no AI SLAs, no monitoring of third-party model changes.
Note on F16: Vendor contracts exist for API access but don't cover AI risks, model changes, or quality guarantees.
Note on G16: Third-party model changes could cause hallucinations. ISO 42001 requires governance of AI supply chain.
Note on H16: Score 2 (Initiated): Vendor relationships exist but AI-specific governance absent.
Note on I16: High: Third-party changes are outside DataVault's control and could cause unexpected behavior.
Note on J16: Vendor AI risk checklist, model change notification requirements, quality SLAs, right-to-audit clauses.
Note on K16: Procurement manages vendor relationships, needs AI governance criteria from technical/compliance teams.
Note on L16: 2.5 months to develop assessment framework and renegotiate agreements.
Note on E17: Basic accuracy tracked but no hallucination rate for InsightEngine, no bias detection for AnomalyDetect.
Note on F17: Accuracy dashboards exist but don't cover hallucination, bias, or drift.
Note on G17: Clause 9.1 requires comprehensive monitoring. Hallucination went undetected because there was no monitoring for it.
Note on H17: Score 2 (Initiated): Basic monitoring exists but critical AI metrics not tracked.
Note on I17: Critical: Monitoring could have detected hallucination before reaching clients. Also needed for AnomalyDetect bias.
Note on J17: Dashboard for: hallucination rate, factual accuracy, bias (demographic, socioeconomic), drift, automated alerting.
Note on K17: CDO oversees data quality and AI performance. ML Ops implements infrastructure.
Note on L17: 2 months — urgent. Monitoring is preventive control against future incidents.
Note on E18: No systematic internal audit for AI. Governance gaps were discovered by a CLIENT audit, not DataVault internally.
Note on F18: No AI audit plans, reports, or findings registers. Only investigation was reactive after hallucination.
Note on G18: That a client found gaps before DataVault did is a significant maturity issue. Internal audits should catch these first.
Note on H18: Score 1 (Not Started): No internal audit capability for AI governance.
Note on I18: High: Internal audits should find issues before external parties. Also required for ISO 42001 certification.
Note on J18: Audit program covering all ISO 42001 clauses with quarterly cycle, trained auditors, findings tracking.
Note on K18: Internal Audit should be independent from AI development for objectivity.
Note on L18: 3.5 months to design program, train auditors, conduct first cycle.
Note on E19: Hallucination investigated informally — no formal RCA, no CAPA process, no systematic corrective action tracking.
Note on F19: Informal incident notes and team discussion but no formal RCA document, CAPA record, or corrective action register.
Note on G19: Clause 10.1 requires formal process for nonconformities. Informal response didn't prevent recurrence or drive improvement.
Note on H19: Score 2 (Initiated): Incident addressed reactively but no formal process for future incidents.
Note on I19: Critical: Without formal incident management, can't demonstrate learning or preventing recurrence.
Note on J19: Establish: incident reporting, root cause analysis methodology, corrective action planning, effectiveness verification, lessons-learned database.
Note on K19: Risk Officer owns CAPA with support from Quality Assurance for methodology and tracking.
Note on L19: 2 months. The hallucination provides a real case to validate the CAPA process against.

## Readiness Dashboard
Control Area | Controls Assessed | Avg Readiness Score | Readiness % | Certification Readiness
AI Policy | 3 | 2 | 40.0% | Not Ready
Planning | 4 | 1.5 | 30.0% | Not Ready
Support | 4 | 1.75 | 35.0% | Not Ready
Operations | 3 | 1.67 | 33.3% | Not Ready
Performance | 2 | 1.5 | 30.0% | Not Ready
Improvement | 1 | 2 | 40.0% | Not Ready
OVERALL READINESS | 17 | 1.71 | 34.1% | Not Ready (Target: ≥80%)
Readiness Score Scale:
1 = Not Started ¦ 2 = Initiated ¦ 3 = In Progress ¦ 4 = Implemented ¦ 5 = Optimized
Note on D2: AI Policy at 40% because leadership memo exists (C5.1.1=2) but no formal policy (C5.1.2=1), roles partially defined (C5.2.1=3), and no competence framework (C5.2.2=1).
Note on D3: Planning at 30% — weakest area. No risk methodology (C6.1.1=1), reactive risk docs (C6.1.2=2), weak objective alignment (C6.2.1=2), and no change management (C6.3.1=1).
Note on D4: Support at 35%. Resources initiated (C7.1.1=2), no training (C7.2.1=1), no awareness program (C7.3.1=2), and partial documentation (C7.4.1=2).
Note on D5: Operations at 33%. Partial lifecycle (C8.1.1=2), no impact assessment (C8.2.1=1), and minimal vendor governance (C8.3.1=2).
Note on D6: Performance at 30%. Basic monitoring only (C9.1.1=2) and no internal audit (C9.2.1=1). The client audit exposed this gap.
Note on D7: Improvement at 40%. Incident was addressed (C10.1.1=2) but informally — no formal CAPA process exists.
Note on D9: Overall 34.1% — well below the 80% certification threshold. DataVault needs significant improvement across all areas, particularly Planning and Performance.

## ISO 42001 Clause Reference
ISO/IEC 42001 Clause Reference
Clause 4 | Context of the Organization | Understanding organizational roles, responsibilities, and strategic objectives related to AI
Clause 5 | Leadership & Governance | Leadership commitment, policies, roles, and organizational structure for AI management
Clause 6 | Planning | Risk assessment, objectives, and change management for AI systems
Clause 7 | Support | Resources, competence, training, and documentation for AI governance
Clause 8 | Operations | AI lifecycle management, impact assessment, and supplier governance
Clause 9 | Performance Evaluation | Monitoring, measurement, and internal audit of AI systems
Clause 10 | Improvement | Nonconformity management, corrective actions, and continuous improvement
Readiness Scoring Scale:
1 | Not Started | No activities or evidence of this control
2 | Initiated | Initial activities underway; partial evidence
3 | In Progress | Formal processes defined and partially implemented
4 | Implemented | Control fully implemented and operating
5 | Optimized | Control continuously improved and optimized
Certification Threshold:
Target: Average Readiness Score ≥ 4.0 (80%+) across all control areas